Below is a discussion-ready extraction of the contract’s core deal terms, then a risk/benefit review from the Landowner’s side, including oversight, equity shift, and what really happens if the Developers default.

1) Core deal terms (what the agreement is really saying)

Parties / Property

- Landowner: Tony

- Developers: RC Brown Homes (1st) + Lazovar Nigeria Limited (2nd)

- Property: 12 Babatunde Jose Rd, Victoria Island, Lagos; ~1,331.474 sqm; land certificate (1974), title no. LO7207.

Project

- Primary scheme: 10-floor mixed-use building (incl ground floor) with:

  - 25 x 2-bedroom flats (each: study + BQ)

  - 2 x 4-bedroom penthouses (each: terrace + study + 2 BQs)

  - 2 floors of office space (2nd & 3rd floors)

- Timeline: total 27 months from execution (3 months approvals + 24 months construction), but also phrased as 24 months from permit + possession.

Sharing / Allocation

On completion:

- Landowner gets: 15 of the 2-bed flats + 1 penthouse (total 16 residential units)

- Developers get: 10 of the 2-bed flats + 1 penthouse + 2 floors office space

- Floors are pre-assigned (Landowner: 5th, 6th, 8th; Developers: 4th, 7th; offices: 2nd & 3rd; penthouses: 9th split).

Cash to Landowner (“Relocation grant / premium”)

- Developers pay ₦200,000,000 in tranches:

  - ₦120m by June 15, 2025

  - ₦30m by July 15, 2025

  - ₦50m by first week of Sept 2025

- Purpose: relocate church + school.

Title / “Trustee/Custodian” structure

- Legal title and key documents to be held by a jointly appointed Trustee/Custodian.

- Important: Landowner must pre-sign Deeds of Assignment for the Developers’ allocated units and deposit them with the Trustee to be released after the Developers fulfill terms.

Control & oversight during construction

- Developers have “overall supervisory control.”

- Landowner may appoint a Building Consultant/Consulting Engineer with access at all times to monitor compliance.

- Landowner also has an inspection right “at any time.”

Defects / Warranty

- Cosmetic defects: Developers fix if reported within 1 year after completion.

- Structural/material defects: Developers responsible and must assess within a week of notice and remedy within “shortest time possible per industry standard.”

Delay / extension

- If delay due to “agreed modification/variations or otherwise,” extension can be “reasonable.”

- Developers must give 1 month notice before completion date; Landowner can grant 3 months, renewable for another 3 months.

Dispute resolution

Negotiation → mediation via LMDC → arbitration under Nigerian Arbitration and Mediation Act 2023.

Termination & consequences

- Termination triggers include: encumbrance/third-party claim, compulsory acquisition, Developers fail quality standard, or fail to complete by completion date/extended date.

- If terminated due to Developer breach, parties appoint QS/valuer; Landowner refunds Developers the assessed value of work done (and “without prejudice to other remedies”).

2) “How beneficial is it to the Landowner?” (headline take)

Potentially attractive upside, but the Landowner is taking major execution/default risk.

What’s good for the Landowner

- Landowner contributes land only; Developers fund construction/approvals (on paper).

- Landowner receives ₦200m cash (relocation) + 16 prime units in VI.

- Sharing ratio is locked even if costs overrun (Clause 10).

What’s risky / where the Landowner is exposed

- The Landowner is effectively “all-in” on Developers performing, yet:

  - No strong performance security (no performance bond, bank guarantee, parent guarantee, escrow, or registered charge).

  - Default remedy is economically painful: Landowner may have to refund the value of work done to take the project back.

  - The pre-signed deeds create a serious “title leakage” risk if release conditions aren’t airtight.

Bottom line: The deal can be great if the Developers are strong and tightly controlled legally; otherwise the Landowner’s downside is big.

3) Does the development shift the Landowner’s “equity”/power position?

Yes—the Landowner’s practical power reduces after possession is handed over, even though they retain ownership interest.

Before possession

- Landowner has full control of land and title.

After possession + demolition begins

- Developers have “overall supervisory control,” and will likely control:

  - contractor selection, procurement, program schedule, site decisions

- Landowner’s role becomes monitoring rather than decision-making, unless the agreement adds explicit consent rights.

Biggest “equity shift” clause

- The title is to be held by a Trustee, and Landowner pre-signs assignments for Developers’ units.

- That means the Landowner is giving away future transfer documents upfront, relying on contractual enforcement to prevent misuse.

4) Does the Landowner have real oversight in the building process?

Some access, but not strong “control.”

What the agreement gives:

- Landowner inspection rights “at any time.”

- Landowner may appoint a consultant with full site access to “work in conjunction” with Developer/PM.

- Developers must inform Landowner of zoning/planning amendments within 5 working days.

What it does not clearly give (this is important):

- No clear right for Landowner/consultant to approve:

  - design changes, material substitutions, value engineering, contractor changes, program changes

- “Certificate of completion” is largely Developer-driven, and Landowner must confirm satisfaction within 3 working days (tight timeline that can be used against Landowner).

- No clear, measurable QA/QC acceptance process (snag list protocol, testing/commissioning standards, independent certification triggers, etc.).

Practical effect: Landowner can “watch” and complain, but may struggle to “stop” decisions.

5) What happens if the Developers default? (as written)

Default process

- Notice of breach → 30 days to remedy → termination right.

If terminated due to Developer breach

- QS/valuer assesses value of work done.

- Landowner “only refunds” assessed value of work done to Developers.

Why this is a problem for Landowner

- Refund obligation can be enormous.
If Developers have spent billions (even inefficiently), Landowner may need to raise huge funds to terminate and regain control.

- No clear step-in/right-to-complete mechanism.
The contract doesn’t clearly say Landowner can take over contractor appointments, designs, permits, or continue works smoothly.

- No clear “security package” for Landowner.
If Developers walk away, the Landowner could be left with:

  - a demolished site,

  - partially completed structure,

  - liens/claims from contractors,

  - and a big refund obligation.

- No clear rule that Developers cannot encumber the land.
There is no strong “no mortgage/no charge/no lien” language visible here, and no requirement that any lender sign a deed of subordination to protect the Landowner.

6) Key concerns / red flags (stuff I would fix before signing)

A) Document quality / internal inconsistencies (signals execution risk)

- The definition of “Premium” says ₦200,000,000 (two million naira) — that’s a serious typo.

- Clause cross-references are off (e.g., “Clause 24” where it should be “Clause 21,” etc.).

- These errors matter because they create interpretation gaps in disputes.

B) Pre-signed deeds + Trustee mechanism = high-risk unless tightened

- The Landowner is signing transfer documents in advance for the Developers’ units.

- If the Trustee release conditions are not extremely strict and objective, you can lose leverage.

Fix conceptually: release should be tied to independent completion milestones, not just “both parties confirm,” and Trustee instructions should be separately documented, precise, and irrevocable.

C) Delay regime is weak (no real penalties)

- Landowner can grant extensions, but there is no liquidated damages / compensation for delay.

- Developers can blame “modifications/variations or otherwise” (that “or otherwise” is dangerously broad).

D) Termination economics are unfavorable to Landowner

- Landowner may have to refund “value of work done” even if:

  - work is defective,

  - over-priced,

  - not aligned with specs,

  - or not legally regularized.

- There’s no clear mechanism for deducting:

  - cost to rectify defects,

  - cost to complete,

  - penalties,

  - third-party claims.

E) Insurance clause needs Landowner protection

- Developers must insure, but it’s not clearly stating:

  - who the beneficiary/loss payee is,

  - whether Landowner is named as co-insured,

  - how proceeds are controlled (Developer “shall apply” is not enough).

F) Sales/marketing and cashflow control is unclear

- The Developers will naturally want to pre-sell units (especially their own).
The contract should be explicit on:

  - whether Developers can sell before completion,

  - whether sale proceeds must be applied to construction,

  - whether Landowner has approval rights on pricing/branding/agents for Landowner units.

G) Force majeure is very broad

- Includes “political unrest, insecurity… aggressive government exchange policies.”
This can become an excuse for non-performance without clear limits.

H) Landowner indemnities are heavy

- Landowner indemnifies Developers for title defects and also losses linked to Landowner’s consultant.
This may be fair in parts, but it needs balancing.

I) Management of common areas / service charge / estate governance not defined

- Who controls facility management after completion?

- How are service charges set?

- Who appoints the facility manager?

- What happens if Developers still own offices and some flats—who controls the management company?

7) Quick scorecard (Landowner-friendly vs Developer-friendly)

Landowner-friendly

- 16 residential units + ₦200m relocation

- cost overruns don’t change sharing ratio

- consultant access and inspection rights

- defect obligations stated

Developer-friendly / Landowner-risky

- Developers control construction decisions

- weak delay penalties

- pre-signed deeds

- termination refund obligation

- unclear anti-encumbrance / financing protections

- acceptance timeline (3 working days) is tight

8) Practical negotiation upgrades (highest impact)

If you want to make this safer for the Landowner, the biggest upgrades are:

- Performance security: bank guarantee/performance bond/parent company guarantee.

- No encumbrance clause + lender subordination: Developers cannot mortgage/charge the land; any construction finance lender must sign protections for Landowner.

- Milestone-based trustee release: deeds released only upon objective milestones + independent certification (QS/Engineer).

- Delay damages: monthly penalty or unit reallocation trigger if delays exceed X months (beyond force majeure).

- Termination formula that protects Landowner: refund = value of compliant work minus defects/rectification/completion costs/claims.

- Stronger Landowner consent rights: material changes, substitutions, design variations, appointment of key contractors.

- Insurance improvements: Landowner as co-insured + loss payee; proceeds controlled via escrow/trustee.